## Group Diary
ItSE Group Work Diary Form |  |  |  | ItSE Group Work Diary Form
Team #/Name:
Student Name | Email | Work Diary Agreed Tasks | weeks | Phase | Task | Task2 | Allocate To | Predecessor Task | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | Status
David Adegeloye | c2020232@hallam.shu.ac.uk | Front-end Stuff. We'll go into more detail later | week 2 |  | Project Scope |  | Abdirizak Mumin/Igor Jankowski/Odi Ehimuan/David Adegeloye
Odi Ehimuan | c3018521@hallam.shu.ac.uk | Front-end Stuff. We'll go into more detail later | week 3 | Completed | Task 1: Define User roles |  | Abdirizak Mumin |  | TBD | TBD | TBD | TBD | Completed
Igor Jankowski | c2053730@hallam.shu.ac.uk | Back-end Stuff. We'll go into more detail later
Abdirizak Mumin | c1053702@hallam.shu.ac.uk | Back-end Stuff. We'll go into more detail later | week 3 | Completed | Define Personas | Define Scenarios |  |  | TBD | TBD | TBD | TBD
|  |  | week 3 | Completed | Define User Stories | Detail user story acceptance criteria | Abdirizak Mumin/Igor Jankowski/Odi Ehimuan/David Adegeloye |  | TBD | TBD | TBD | TBD | Completed
|  |  | week 4 | Plainning | Use case diagram |  | Abdirizak Mumin/Igor Jankowski |  | TBD | TBD | TBD | TBD | Uncompleted
Note: List all tasks seperated by commas for each member. |  |  | week 4 | Plainning | Creates. the wire frame or prototype. |  | Abdirizak Mumin/David Adegeloye | Abdirizak Mumin/ Odi Ehimuan | TBD | TBD | TBD | TBD | Uncompleted
|  |  |  | planning | Building Front-end of website |  | Odi Ehimuan/David Adegeloye |  | TBD | TBD | TBD | TBD
|  |  |  | planning | Building Back-end of website |  | Abdirizak Mumin/Igor Jankowski | Odi Ehimuan | TBD | TBD | TBD | TBD